## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the milestone description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use the progress column to add how much of the project you finished by adding a percentage number • Add the day you started your project in the start date column • Finish your calculations by filling in the number of days you need to complete your project in the days column

## Green
Project: Green
Contoso, Ltd.
Riku Nakano
Project start date: | 2025-10-01 | [10 empty] | Scrolling increment: | [5 empty] | 0
Milestone marker: | 1 |  |  |  | October | [34 empty] | November
 | time axis 2025-10-01 to 2025-11-25
Milestone description | Progress | Column1 | Start | Days | time axis 2025-10-01 to 2025-11-25
Project development
Planning & Research | 100% |  | 2025-10-01 | 8
Data Preprocessing | 100% |  | 2025-10-07 | 8
Model Training | 100% |  | 2025-10-10 | 15
URL Extractor | 100% |  | 2025-10-17 | 11
Chain Implementation | 100% |  | 2025-10-25 | 10
Quarantine & Logging | 100% |  | 2025-10-31 | 8
Pop-ups & UI | 100% |  | 2025-11-05 | 9
Dashboard | 100% |  | 2025-11-12 | 8
Testing & Evaluation | 100% |  | 2025-11-17 | 10
Future - Maintenance | 0%
To add more data, Insert new rows ABOVE this one

## Blue
Project: Blue
Contoso, Ltd.
Gurpreet Bawa
Project start date: | 2025-11-28 | [10 empty] | Scrolling increment: | [5 empty] | 13
Milestone marker: | 1 | 1 |  |  | December | [20 empty] | January
 | time axis 2025-12-11 to 2026-02-04
Milestone description | Assigned to | Progress | Start | Days | time axis 2025-12-11 to 2026-02-04
Title 1
Task 1 |  | 25% | 2025-12-01 | 3
Task 2 |  |  | 2025-12-06 | 1
Task 3 |  | 50% | 2025-11-28 | 10
Task 4 |  |  | 2025-12-21 | 1 | bar: 2025-12-21
Task 5 |  | 10% | 2025-12-07 | 6
Title 2
Task 1 |  | 60% | 2025-12-07 | 13
Task 2 |  | 50% | 2025-12-08 | 9
Task 3 |  | 33% | 2025-12-16 | 11
Task 4 |  |  | 2025-12-25 | 1 | bar: 2025-12-25
Task 5 |  |  | 2025-12-26 | 24
Title 3
Task 1 |  |  | 2025-12-16 | 4
Task 2 |  |  | 2025-12-20 | 14
Task 3 |  |  | 2026-01-05 | 6
Task 4 |  |  | 2026-01-18 | 3
Task 5 |  |  | 2026-01-10 | 19
Title 4
Task 1 |  |  | 2026-01-07 | 15
Task 2 |  |  | 2025-12-30 | 5
Task 3 |  |  | 2026-02-19 | 5
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Purple
Project: Purple
Contoso, Ltd.
Hayden Cook
Project start date: | 2025-11-28 | [10 empty] | Scrolling increment: | [5 empty] | 13
Milestone marker: | 1 | 1 |  |  | December | [20 empty] | January
 | time axis 2025-12-11 to 2026-02-04
Milestone description | Assigned to | Progress | Start | Days | time axis 2025-12-11 to 2026-02-04
Title 1
Task 1 |  | 25% | 2025-12-01 | 3
Task 2 |  |  | 2025-12-06 | 1
Task 3 |  | 50% | 2025-11-28 | 10
Task 4 |  |  | 2025-12-21 | 1 | bar: 2025-12-21
Task 5 |  | 10% | 2025-12-07 | 6
Title 2
Task 1 |  | 60% | 2025-12-07 | 13
Task 2 |  | 50% | 2025-12-08 | 9
Task 3 |  | 33% | 2025-12-16 | 11
Task 4 |  |  | 2025-12-25 | 1 | bar: 2025-12-25
Task 5 |  |  | 2025-12-26 | 24
Title 3
Task 1 |  |  | 2025-12-16 | 4
Task 2 |  |  | 2025-12-20 | 14
Task 3 |  |  | 2026-01-05 | 6
Task 4 |  |  | 2026-01-18 | 3
Task 5 |  |  | 2026-01-10 | 19
Title 4
Task 1 |  |  | 2026-01-07 | 15
Task 2 |  |  | 2025-12-30 | 5
Task 3 |  |  | 2026-02-19 | 5
Task 4
Task 5
To add more data, Insert new rows ABOVE this one